## Sheet1
Project Title | Week-1 | Week-2 | Week-3 | Week-4 | Week-5 | Week-6 | Week-7 | Week-8 | Week-9 | Week-10 | Week-11 | Week-12 | Week-13 | Week-14 | Week-15
Jenkins-Based Podcast Episode Release System | Problem Definition and Scope: Study the real-time need for the Podcast Episode Release System. Identify target users, existing pain points, stakeholders, constraints and measurable success criteria. Freeze a small 15-week MVP scope. Deliverable: Problem statement, stakeholder list, objectives, constraints and approved MVP scope. | Agile Planning and DevOps Workflow: Create user stories and acceptance criteria for the Podcast Episode Release System. Prepare a product backlog, 15-week Kanban/Scrum plan, Definition of Done and a DevOps lifecycle diagram from development to operations. Deliverable: Backlog, task board, sprint plan, Definition of Done and DevOps workflow diagram. | Requirements, Architecture and Technology Setup: Design the minimum application architecture for the Podcast Episode Release System. The MVP should cover create, view, update and search records; role-based status workflow; summary dashboard. Select the programming stack, Maven/Gradle/Ant build tool, database if required, Tomcat/Nginx deployment target and local development setup. Deliverable: SRS summary, use-case diagram, architecture diagram, data model/API list and working local setup. | Git and GitHub Repository Initialization: Create a GitHub repository for the Podcast Episode Release System. Add README, .gitignore, folder structure, issue templates and branch naming rules. Commit the initial application skeleton using meaningful commit messages. Deliverable: Repository URL, README, initial commits, issues and branch policy. | Feature Development with Branching: Implement the first core workflow of the Podcast Episode Release System on a feature branch. Use add, commit, push, pull and logs. Raise a pull request, review changes and merge into the development branch. Deliverable: Working feature 1, feature branch, pull request, review comments and merge evidence. | MVP Completion and Git Collaboration: Implement the remaining essential MVP functions for the Podcast Episode Release System: create, view, update and search records; role-based status workflow; summary dashboard. Demonstrate a second feature branch, conflict creation/resolution, tagging and a release-ready source baseline. Deliverable: Functional MVP, resolved merge conflict, tagged version and updated backlog. | Jenkins Installation and Continuous Integration Job: Install and configure Jenkins. Connect the Podcast Episode Release System GitHub repository and create a Maven/Gradle/Ant build job triggered by commit or scheduled polling. Archive the build artefact. Deliverable: Configured Jenkins job, successful build log, trigger evidence and archived artefact. | Pipeline as Code and Server Deployment: Create a Jenkinsfile for the Podcast Episode Release System with checkout, build, package and deploy stages. Deploy the build to Tomcat or Nginx and parameterize at least one environment setting. Deliverable: Jenkinsfile, successful pipeline run, deployed application URL/screenshot and configuration evidence. | Selenium Test Design and Local Execution: Identify three to five critical user journeys in the Podcast Episode Release System. Write Selenium WebDriver test cases with assertions, test data and screenshots for failures. Execute the suite locally through Maven. Deliverable: Test plan, Selenium scripts, local test report and failure screenshot mechanism. | Continuous Testing in Jenkins: Integrate the Podcast Episode Release System Selenium suite into Jenkins. Publish test reports and configure the pipeline so failed tests stop deployment. Correct at least one deliberately introduced defect and rerun the pipeline. Deliverable: Jenkins test report, failed pipeline evidence, defect correction commit and successful rerun. | Docker Image and Container Lifecycle: Create a Dockerfile for the Podcast Episode Release System. Build and tag the image, run the container, map ports, inspect logs, stop/restart/remove containers and document the complete container lifecycle. Deliverable: Dockerfile, image details, Docker command log and running container evidence. | Jenkins-Docker Continuous Deployment: Extend the Podcast Episode Release System Jenkins pipeline to build a versioned Docker image, publish it to Docker Hub or a local registry and deploy a fresh container automatically after successful tests. Deliverable: Versioned image, registry evidence and end-to-end commit-to-container pipeline. | Configuration Management Script: Identify all server prerequisites for the Podcast Episode Release System: packages, users, folders, files, ports and services. Create either a Puppet manifest/modules or an Ansible inventory and YAML playbook to configure the target node. Deliverable: Configuration specification, Puppet manifest or Ansible playbook and first execution log. | Automated Provisioning and Reliability Validation: Provision a clean target environment for the Podcast Episode Release System using Puppet/Ansible. Deploy the application or container, rerun the automation to demonstrate idempotency, perform a health check and test rollback/recovery to the previous stable release. Deliverable: Provisioned node, idempotency evidence, health-check result and rollback/recovery demonstration. | Final End-to-End Release, Documentation and Viva: Run the complete Podcast Episode Release System DevOps workflow from Git commit to Jenkins build, Selenium quality gate, Docker deployment and Puppet/Ansible provisioning. Complete technical documentation, architecture, troubleshooting guide, limitations and future enhancement plan. Deliverable: Final repository, live demonstration, complete report, screenshots/video, presentation and viva.