Jenkins-Based Podcast Episode Release System

Week 2: Agile Planning and DevOps Workflow

# 1. Product Backlog

Prioritized using MoSCoW (Must / Should / Could / Won't) and sized in story points.

| ID | User Story | Priority | Est. (pts) | Sprint (Week) |
| --- | --- | --- | --- | --- |
| US-01 | As a Producer, I want to create a new episode record with audio file + metadata, so that I can start a release | Must | 5 | 5 |
| US-02 | As a Producer, I want to view a list of episode records with their status, so that I can track progress | Must | 3 | 5 |
| US-03 | As a Producer, I want to update episode metadata before release, so that I can fix errors | Must | 3 | 6 |
| US-04 | As a Producer, I want to search/filter episodes by title, date, or status, so that I can find a specific record quickly | Must | 3 | 6 |
| US-05 | As an Admin, I want role-based access (Producer, Host, Admin), so that only authorized users change release status | Must | 5 | 6 |
| US-06 | As a Producer, I want an episode to move through a status workflow (Draft to Validated to Published to Failed), so that everyone knows release state | Must | 5 | 6 |
| US-07 | As a Host/Admin, I want a summary dashboard showing episode counts by status, so that I get an at-a-glance view | Must | 3 | 7 |
| US-08 | As a Producer, I want the system to validate audio format/metadata before allowing Publish, so that bad releases are prevented | Must | 5 | 7 |
| US-09 | As a DevOps Admin, I want the app packaged and deployable via a Maven/Gradle build, so that Jenkins can build it | Must | 3 | 8 |
| US-10 | As a DevOps Admin, I want a Jenkins CI job triggered on commit, so that every change is auto built | Must | 5 | 8 |
| US-11 | As a DevOps Admin, I want a Jenkinsfile with build/test/deploy stages, so that the release pipeline is code-defined | Must | 5 | 9 |
| US-12 | As a QA, I want Selenium tests for core user journeys, so that regressions are caught | Should | 8 | 10-11 |
| US-13 | As a DevOps Admin, I want the app containerized via Docker, so that deployment is environment-independent | Should | 5 | 12-13 |
| US-14 | As a DevOps Admin, I want automated configuration management (Ansible/Puppet), so that server setup is repeatable | Should | 5 | 14 |
| US-15 | As a Host, I want an email/Slack notification on release success or failure, so that I do not need to check manually | Could | 3 | 9 |
| US-16 | As a DevOps Admin, I want rollback to the last known-good release, so that bad releases can be reverted quickly | Should | 5 | 14 |
| US-17 | As a Producer, I want audit logs of every status change, so that I can trace who did what | Could | 3 | 15 |

## Won't-have (MVP)

- Multi-show / multi-tenant support

- Social media automation

- AI-generated show notes

- Analytics/listener metrics dashboard

# 2. Kanban Task Board

Board columns used for daily tracking during each sprint week:

| Backlog | Ready | In Progress | In Review / Testing | Done |
| --- | --- | --- | --- | --- |

WIP limit: maximum 2 items "In Progress" per person, to avoid context-switching on a small team.

# 3. 15-Week Sprint Plan

One-week sprints aligned to the course schedule, Scrum-flavored with daily Kanban tracking.

| Week | Sprint Goal | Backlog Items |
| --- | --- | --- |
| 1 | Foundation: repo, README, skeleton | Setup tasks (pre-backlog) |
| 2 | Agile planning artifacts | This deliverable |
| 3 | Architecture and local setup | SRS, use-case, architecture, DB/API design |
| 4 | Repo and branching policy live | Repo init, issue templates, branch rules |
| 5 | Feature 1: Create + View records | US-01, US-02 |
| 6 | MVP core complete | US-03, US-04, US-05, US-06 |
| 7 | Dashboard and validation | US-07, US-08 |
| 8 | Jenkins CI | US-09, US-10 |
| 9 | Pipeline as code + deploy | US-11, US-15 |
| 10 | Selenium test design | US-12 (design + local run) |
| 11 | Continuous testing in Jenkins | US-12 (Jenkins integration) |
| 12 | Docker lifecycle | US-13 |
| 13 | Jenkins-Docker CD | US-13 (pipeline integration) |
| 14 | Configuration management | US-14, US-16 |
| 15 | Final release, docs, viva | US-17, documentation |

# 4. Definition of Done (DoD)

An item is "Done" only when all of the following are true:

- Code is committed to the correct feature branch with meaningful commit messages.

- Pull request raised, reviewed by at least one other team member (or self-review checklist if solo), and merged to develop.

- Unit/manual test evidence exists (screenshot or test report) for the acceptance criteria.

- No known critical/blocker defects remain open against the story.

- Relevant documentation updated (README, API list, or architecture doc as applicable).

- Build passes locally, and from Week 8 onward, passes the Jenkins CI job.

- Feature demoed/verified against its acceptance criteria before marking Done on the board.

# 5. Acceptance Criteria (Sample Core Stories)

## US-01: Create episode record

- Given I am a logged-in Producer, when I submit title, audio file, publish date and description, then a new record is created with status = Draft.

- Given that required fields are missing, when I submit, then the system shows a validation error and does not create the record.

## US-06: Status workflow

- Given an episode is in Draft, when validation passes, then status moves to Validated.

- Given an episode is Validated, when the release pipeline succeeds, then status moves to Published.

- Given the release pipeline fails, then status moves to Failed and cannot skip to Published.

- Only Admin/Host roles can manually override a status.

## US-08: Pre-publish validation

- Given an audio file is not in an accepted format, when Publish is attempted, then the system blocks publish and shows the reason.

- Given the required metadata (title, date, description) is missing, then Publish is blocked.

# 6. DevOps Workflow:

End-to-end lifecycle the release pipeline follows, from a developer's commit through to a monitored, running production container.